## Pilot register
RecordID | Title | ItemType | Status | Priority | OwnerRole | DueDate | Gate | SourceDocument | EvidenceRequired | DependencyID | AsOfDate | DataClassification
R01 | Triage recommendation lacks source evidence | Risk | Open | High | Risk lead | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | Reference coverage and source-fidelity test results; no material unsupported recommendation | A04 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R02 | Handlers accept recommendations without challenge | Risk | Open | High | Operations lead | 2026-10-03 | Before launch | 07-Triage-Process-and-Exceptions.docx | Observed override and escalation rehearsal; training evidence | A06 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R03 | Subgroup errors are hidden by aggregate accuracy | Risk | Open | High | Independent evaluation lead | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | Segmented test report and documented limitations for small samples | A04 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R04 | Vendor retention and change terms remain unresolved | Risk | Blocked | High | Procurement lead | 2026-10-02 | Before launch | 08-Architecture-and-Data-Boundaries.docx | Reviewed retention, access, model-change and exit terms | A08 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R05 | Faster triage increases rework downstream | Risk | Open | Medium | Claims quality lead | 2026-11-04 | Day 30 | 06-Service-Operations-Review.docx | Rework and queue-aging comparison adjusted for intake mix | A10 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R06 | Released time is presented as cash savings | Risk | Mitigated | High | Finance partner | 2026-10-05 | Committee decision | 04-Finance-Assumptions.docx | Capacity wording retained in approved presentation and benefit definitions | A02 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R07 | All 240 handlers are assumed productive on day one | Risk | Open | Medium | Change lead | 2026-10-04 | Before launch | 10-Capacity-and-Adoption-Plan.docx | Wave roster and ramp sensitivity; no guaranteed realization | A07 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R08 | Pilot scope expands into claim decisions | Risk | Mitigated | High | Sponsor | 2026-10-03 | Before launch | 07-Triage-Process-and-Exceptions.docx | Purpose statement and enforced exclusion of rejection, settlement and payment | A06 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R09 | Reference documents contain stale instructions | Risk | Open | Medium | Data owner | 2026-10-02 | Before launch | 08-Architecture-and-Data-Boundaries.docx | Approved-source inventory, version and retirement procedure | A03 | 2026-09-30 | Fictional workshop data - not ERGO operating data
R10 | Pilot is evaluated by its own delivery team only | Risk | Open | High | Independent evaluation lead | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | Named independent reviewer and challenge record | A12 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A01 | Freeze the month-end data definitions | Action | Closed | Medium | Data owner | 2026-09-22 | Committee decision | 06-Service-Operations-Review.docx | Dictionary reviewed; backlog is stock and CSAT is response weighted |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A02 | Publish the controlling finance assumptions | Action | Closed | High | Finance partner | 2026-09-24 | Committee decision | 04-Finance-Assumptions.docx | 15% base and 10% downside replace the earlier 25% estimate |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A03 | Confirm the approved evaluation-data inventory | Action | Open | High | Data owner | 2026-09-27 | Before launch | 08-Architecture-and-Data-Boundaries.docx | Inventory, permissions, provenance and retention reviewed |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A04 | Assemble the independent evaluation reference set | Action | Blocked | High | Independent evaluation lead | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | 800 proposed test cases; labeled expected routes and evidence references | A03 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A05 | Agree triage reason codes and queue ownership | Action | In progress | Medium | Operations lead | 2026-10-01 | Before launch | 07-Triage-Process-and-Exceptions.docx | Queue owner, handover and uncertainty reason codes signed off |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A06 | Rehearse human override and manual fallback | Action | Open | High | Claims quality lead | 2026-10-03 | Before launch | 07-Triage-Process-and-Exceptions.docx | Observed rehearsal with out-of-scope and missing-evidence cases | A05 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A07 | Confirm the three-wave training roster | Action | In progress | Medium | Change lead | 2026-10-04 | Before launch | 10-Capacity-and-Adoption-Plan.docx | Three illustrative waves of 80 handlers; champions and support cover |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A08 | Resolve vendor retention and model-change clauses | Action | Blocked | High | Procurement lead | 2026-09-29 | Before launch | 08-Architecture-and-Data-Boundaries.docx | Written resolution of retention, audit, model changes and exit terms |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A09 | Review least-privilege roles and audit coverage | Action | Open | High | Security lead | 2026-10-03 | Before launch | 08-Architecture-and-Data-Boundaries.docx | Role matrix and sample reconstructed recommendation trace | A03 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A10 | Baseline usable time, rework and service outcomes | Action | Open | High | Finance partner | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | Measurement definitions, comparison cohort and sampling plan | A01 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A11 | Prepare the day-30 stop or continue review | Action | Open | Medium | Sponsor | 2026-11-04 | Day 30 | 05-Risk-and-Decision-Gates.docx | Proposed checkpoint pack; date assumes an unapproved 6 October start | A14 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A12 | Name an independent evaluation reviewer | Action | Open | High | Risk lead | 2026-10-02 | Before launch | 09-Evaluation-Protocol.docx | Reviewer independence and escalation route documented |  | 2026-09-30 | Fictional workshop data - not ERGO operating data
A13 | Reconcile South Property start with 240-handler scope | Action | Open | High | Operations lead | 2026-10-02 | Committee decision | 10-Capacity-and-Adoption-Plan.docx | Clear distinction between starting queue, eventual handler population and wave ramp | A07 | 2026-09-30 | Fictional workshop data - not ERGO operating data
A14 | Submit a conditional funding decision paper | Action | Open | High | Sponsor | 2026-10-05 | Committee decision | 11-Committee-Working-Session.docx | Cost, unresolved conditions and finance sensitivity; no assumed approval | A08 | 2026-09-30 | Fictional workshop data - not ERGO operating data

## Read me
Purpose | ERGO Claims Pilot - Risks and Actions - DEMO
Classification | Fictional workshop data - not ERGO operating data
Status date | 2026-09-30
Snapshot boundary | Not a live SharePoint connection. Refresh the notebook snapshot after list edits.
Dates | ISO text dates for reliable CSV import. Interpret overdue as of 30 September 2026, not today's date.
Authority | Role names are fictional labels, not assigned tenant people. No funding has been approved.
Expected shape | 24 records: 10 risks, 14 actions; 3 blocked; 2 overdue unclosed actions as of the snapshot.